## TestReport
PFOJECT OVERVIEW
PROJECT BASIC INFORMATION
| Project name | Real estate agent
| Name of Product (Product number) | Real estate brokerage system for the US market
| Product description | Online System
| Project description | <Mision of project> Create a real estate brokerage system to serve the Americans about the land trading. <Project output> Real estate brokerage system
|  | Project type | Trading system
| Project duration | Start day | 2024-05-10 |  | Finish day | 2024-06-03
PREVIEW REPORT
TEST CYCLE
Integration Test
| pass | 43
| fail | 14
| pending | 48
| Total (testcase) | 105
PREVIEW REPORT
| Function | % TCs Executed | % TCs Passed | % TCs Pending
| Sign in | 100% | 66% | 33%
| Sign up | 100% | 53% | 23%
| Buy Properties | 0% | 0% | 0%
| Sell Properties | 0% | 0% | 0%
| Transaction Managed | 0% | 0% | 0%
| Staff Managed | 0% | 0% | 0%
| Customer Managed | 0% | 0% | 0%
| Invitation Managed | 0% | 0% | 0%
| View agent | 0% | 0% | 0%
| View Transaction history | 100% | 0% | 100%
| View on-going transaction | 100% | 0% | 100%
| Type |  |  | Number of bug
| As status |  | Open | 8
|  |  | Cancel | 0
| As Priority |  | low | 1
|  |  | medium | 3
|  |  | high | 4
| As Serverity |  | cosmetic | 1
|  |  | medium | 3
|  |  | serious | 0
|  |  | Fatal | 4
| AS UI/FUNC |  | UI_label/message | 0
|  |  | UI_layout | 1
|  |  | UI_position/size | 0
|  |  | Cod-Logic of code | 1
|  |  | Fun_Feature Missing | 0
|  |  | Fun_Incomplete Function | 6
|  |  | Fun_Wrong Bussiness Logic | 0
| As Level |  | Intergration | 8
|  |  | Acceptance | 0
| As prepare |  | In Testcase | 8
|  |  | Without Testcase | 0
| Total (bug) |  |  | 8
# | Bug description | Screen | QC Activity | Priority | Severity | Defect Type | Pass/Fail | Status | TestCase ID | Bug ID
1 | Create account without agree term | SC_005 | Integration Test | High | Fatal | cod_Logic of Code | fail | open | 24 (SC_005) | 1
2 | GUI_Term of use | SC_005 | Integration Test | Low | Cosmetic | UI Layout | fail | open | 11 (SC_005) | 2
3 | Choose both agent & customer checkbox | SC_005 | Integration Test | Medium | Medium | Fun_Incomplete Function | fail | open | 23 (SC_005) | 3
4 | confirm password | SC_005 | Integration Test | High | Fatal | Fun_Incomplete Function | fail | open | 6 (SC_005) | 4
5 | zipcode text box & phone text box | SC_005 | Integration Test | Medium | Medium | Fun_Incomplete Function | fail | open | 9 - 10 (SC_005) | 5
6 | Create account | SC_005 | Integration Test | High | Fatal | Fun_Incomplete Function | fail | open | 21 (SC_005) | 6
7 | Capcha | SC_005 | Integration Test | Medium | Medium | Fun_Incomplete Function | fail | open | 16 (SC_005) | 7
8 | Login | SC_004 | Integration Test | High | Fatal | Fun_Incomplete Function | fail | open | 13 (SC_005) | 8